Proposed Timeline for 2005 Conference, hosted by Unity Church–Unitarian, St. Paul, Local Arrangements

Summer 2003

Compare hotel sites/costs

November 2003
Sign hotel contract

Summer 2004

Put together conference budget




Create conference “logo”




Recruit co-chairs

July 2004

Meet with Conference Program Committee

August 1, 2004

Mailing for workshop presenters to church leaders





(directed by Program Committee)

August 2004

Preliminary budget to Program Coordinator for consultation




Draft budget to PSD Board for approval (8/27 – 28)




Article to PSD for the September issue of The Prairie Star 





(deadline: 8/23)

September 2004
8.5 x 11 poster for churches to post – to PSD office




Electronic version of poster for PSD website w/reduced-size





version for PSD website for church newsletter editors

October 2004

Meet with Conference Program Committee

Draft of registration brochure to PSD Program Coordinator for





feedback




Recruit volunteers




Firm number of meeting rooms to hotel by November 1

November 2004
Registration brochure to PSD office for approval




Final budget to PSD Board for approval (11/12 – 13)




Continue recruiting volunteers

December 2004

Brochure to Sarah Greene at PSD office




Submit conference promotion to PSD newsletter




On-line registration ready

January 2005

Meet with Conference Program Committee




Hotel team to select meals

 


Mail brochure to individuals and congregations 





(deadline: 1/14)

March 2005

Registration early deadline: March 1

April 8-10, 2005
Annual conference

Revised: 11-15-04
